## Schedule
ID | Issue Type | Summary | Component | Workstream | Owner | Status | Week # | Start Date | Due Date | Description
TH-001 | Story | testo CLI (scan / generate / ask) | CLI | Platform / CLI | Nikhil Vemula | Done | 1 | 2026-05-15 | 2026-05-15 | Command-line entrypoint that orchestrates scan, generate and ask.
TH-002 | Story | Crawler engine (BFS + capture) | Crawler | Discovery & Context | Nikhil Vemula | Done | 1 | 2026-05-18 | 2026-05-18 | Crawlee + Playwright BFS crawler with full network capture, login and safe-click pass.
TH-003 | Story | Graphify code-graph extractor | Context: Content Extractor | Discovery & Context | Nikhil Vemula | Done | 1 | 2026-05-19 | 2026-05-19 | LLM-enriched code knowledge graph (detect -> AST -> semantic).
TH-004 | Story | Set up Jira board, sprints + workflow | Project Mgmt | Project Management | Nikhil Kalsi | Backlog | 1 | 2026-05-15 | 2026-05-19 | Project + board setup.
TH-005 | Story | Graphify run engine | Crawler | Discovery & Context | Nikhil Vemula | Done | 1 | 2026-05-20 | 2026-05-20 | Graphify CLI runner with automatic LLM backend selection.
TH-006 | Story | DB-schema extractor (AST + LLM) | Context: Content Extractor | Discovery & Context | Nikhil Vemula | Done | 1 | 2026-05-21 | 2026-05-21 | Database-schema extractor: deterministic SQLAlchemy AST + LLM for Django/Prisma/TypeORM.
TH-007 | Story | Framework detection + 20+ code-extractors | Context: Content Extractor | Discovery & Context | Nikhil Vemula | Done | 2 | 2026-05-22 | 2026-05-22 | Detects the app framework and runs the matching per-language route/handler extractors.
TH-008 | Story | Mock-data + OpenAPI extractors | Context: Content Extractor | Discovery & Context | Nikhil Vemula | Done | 2 | 2026-05-25 | 2026-05-25 | Distils request/response samples and probes/parses the OpenAPI spec.
TH-009 | Story | Text-kg + Jira + Confluence extractors | Context: Content Extractor | Discovery & Context | Nikhil Vemula | Done | 2 | 2026-05-26 | 2026-05-26 | Extracts knowledge from docs, Jira and Confluence (kg-gen).
TH-010 | Story | Indexer — 13 topics | Context: Indexer/Scan | Discovery & Context | Nikhil Vemula | Done | 2 | 2026-05-27 | 2026-05-27 | Merges every source into 13 indexed topic files (APIs, pages, routes, etc.).
TH-011 | Story | API-spec verifier (authenticity gate) | Context: Indexer/Scan | Discovery & Context | Nikhil Vemula | Done | 2 | 2026-05-28 | 2026-05-28 | LLM check that removes phantom/stripped-prefix endpoints and repairs request bodies.
TH-012 | Story | Intelligent login classifier | Crawler | Discovery & Context | Nikhil Vemula | Done | 3 | 2026-05-29 | 2026-05-29 | One LLM classifier for SSO vs normal login with concrete selectors/steps.
TH-013 | Story | Intent-extraction performance tuning | Crawler | Discovery & Context | Nikhil Vemula | Done | 3 | 2026-06-01 | 2026-06-01 | Dedup + concurrency + row caps cut a 34-page crawl from ~81 min to ~30s.
TH-014 | Story | Wire knowledge-file build into the scan | Context: Indexer/Scan | Core Loop | Ankit | Backlog | 3 | 2026-06-01 | 2026-06-01 | Build the file at the end of a scan.
TH-015 | Story | Route-tree wired into the crawler | Crawler | Discovery & Context | Nikhil Vemula | Done | 3 | 2026-06-02 | 2026-06-02 | Route-tree generation added to the crawler pipeline.
TH-016 | Story | Smoke-test the knowledge file | Tests | Core Loop | Ankit | Backlog | 3 | 2026-06-02 | 2026-06-02 | Verify a scan produces a non-empty file.
TH-017 | Story | Graph viewer (interactive HTML) | Context: Graph Viewer | Discovery & Context | Nikhil Vemula | Done | 3 | 2026-06-03 | 2026-06-03 | Self-contained vis-network HTML graphs (click-graph, ui-routes).
TH-018 | Story | Add provider selection | Infra: Model Connector | Core Loop | Ankit | Backlog | 3 | 2026-06-03 | 2026-06-03 | Register + choose between providers.
TH-019 | Story | API-test generator (verified spec) | Generation | Generation | Nikhil Vemula | Done | 3 | 2026-06-04 | 2026-06-04 | Generates curl API tests from the verified spec with session-safety exemptions.
TH-020 | Story | Smoke-test each model provider | Tests | Core Loop | Ankit | Backlog | 3 | 2026-06-04 | 2026-06-04 | Each provider returns a response.
TH-021 | Story | API-test self-repair loop | Generation | Generation | Nikhil Vemula | Done | 4 | 2026-06-05 | 2026-06-05 | On 422/400, fixes the request body from the server error and re-runs (<=3 attempts).
TH-022 | Story | Add the run command to the CLI | CLI | Core Loop | Ankit | Backlog | 4 | 2026-06-05 | 2026-06-05 | Expose 'testo run'.
TH-023 | Story | OpenAPI write/mutation test-gen | Generation | Generation | Nikhil Vemula | Done | 4 | 2026-06-08 | 2026-06-08 | Spec-driven write/mutation API tests plus execution.
TH-024 | Story | Agentic harness (LLM tool-calling) | Infra: Agentic Harness | Infrastructure | Nikhil Vemula | Done | 4 | 2026-06-09 | 2026-06-09 | OpenHarness wrapper: LLM tool-calling loop, backend resolver, honesty rule.
TH-025 | Story | Build the results dashboard | Execution | Core Loop | Ankit | Backlog | 4 | 2026-06-08 | 2026-06-09 | Pass/fail/flaky + coverage report.
TH-026 | Story | Skill register | Infra: Skill Register | Infrastructure | Nikhil Vemula | Done | 4 | 2026-06-10 | 2026-06-10 | Catalog + service that runs the project's skills uniformly.
TH-027 | Story | Add the report command to the CLI | CLI | Core Loop | Ankit | Backlog | 4 | 2026-06-10 | 2026-06-10 | Expose 'testo report'.
TH-028 | Story | Model connector (MiniMax) | Infra: Model Connector | Infrastructure | Nikhil Vemula | Done | 4 | 2026-06-11 | 2026-06-11 | LLM connector with the MiniMax provider implemented.
TH-029 | Story | Write run results back into the knowledge file | Feedback | Core Loop | Ankit | Backlog | 4 | 2026-06-11 | 2026-06-11 | Record run history (depends A1).
TH-030 | Story | Provenance / confidence schema | Knowledge Base | Knowledge Base | Nikhil Vemula | Done | 5 | 2026-06-12 | 2026-06-12 | Discovery-tier provenance + confidence model used across all sources.
TH-031 | Story | Trigger feedback automatically after a run | Feedback | Core Loop | Ankit | Backlog | 5 | 2026-06-12 | 2026-06-12 | Run write-back when a run finishes.
TH-032 | Story | Add the UI-test generation command | CLI | Core Loop | Ankit | Backlog | 5 | 2026-06-15 | 2026-06-15 | Expose 'testo generate ui-tests'.
TH-033 | Story | Define the knowledge-file structure | Knowledge Base | Core Loop | Nikhil Vemula | Backlog | 5 | 2026-06-16 | 2026-06-16 | Agree facts + source + confidence shape.
TH-034 | Story | Register the UI generator as a skill | Infra: Skill Register | Core Loop | Ankit | Backlog | 5 | 2026-06-16 | 2026-06-16 | Make it discoverable.
TH-035 | Story | Add the plan command to the CLI | CLI | Core Loop | Ankit | Backlog | 5 | 2026-06-17 | 2026-06-17 | Expose 'testo plan'.
TH-036 | Story | Merge indexed outputs into the knowledge file | Knowledge Base | Core Loop | Nikhil Vemula | Backlog | 5 | 2026-06-17 | 2026-06-18 | Combine the 13 topic files into one file.
TH-037 | Story | Add syntax checks for generated tests | Generation | Core Loop | Ankit | Backlog | 5 | 2026-06-18 | 2026-06-18 | Catch broken tests early.
TH-038 | Story | Add knowledge-file read/write helpers | Knowledge Base | Core Loop | Nikhil Vemula | Backlog | 6 | 2026-06-19 | 2026-06-19 | Safe load/save/append helpers.
TH-039 | Story | Run the validator before execution | Generation | Core Loop | Ankit | Backlog | 6 | 2026-06-19 | 2026-06-19 | Block bad tests from the runner.
TH-040 | Story | Add OpenAI model provider | Infra: Model Connector | Core Loop | Nikhil Vemula | Backlog | 6 | 2026-06-22 | 2026-06-22 | Use OpenAI models.
TH-041 | Story | Fold merged records into the knowledge file | Knowledge Base | Context Analytics | Ankit | Backlog | 6 | 2026-06-22 | 2026-06-22 | Write de-duplicated records back.
TH-042 | Story | Add local (Ollama) model provider | Infra: Model Connector | Core Loop | Nikhil Vemula | Backlog | 6 | 2026-06-23 | 2026-06-23 | Local models for offline use.
TH-043 | Story | Add written-doc knowledge to the knowledge file | Knowledge Base | Context Analytics | Ankit | Backlog | 6 | 2026-06-23 | 2026-06-23 | Include docs/Jira/Confluence knowledge.
TH-044 | Story | Add Anthropic model provider | Infra: Model Connector | Core Loop | Nikhil Vemula | Backlog | 6 | 2026-06-24 | 2026-06-24 | Use Anthropic models.
TH-045 | Story | Run analytics as part of a scan | Context: Indexer/Scan | Context Analytics | Ankit | Backlog | 6 | 2026-06-24 | 2026-06-24 | Wire analytics into the scan.
TH-046 | Story | Run feature grouping in the scan | Context: Indexer/Scan | Context Analytics | Ankit | Backlog | 6 | 2026-06-25 | 2026-06-25 | Wire feature grouping in.
TH-047 | Story | Run the generated UI tests + emit JSON | Execution | Core Loop | Nikhil Vemula | Backlog | 6 | 2026-06-25 | 2026-06-26 | Execute Playwright specs with machine-readable output.
TH-048 | Story | Run gap analysis in the scan | Context: Indexer/Scan | Context Analytics | Ankit | Backlog | 7 | 2026-06-26 | 2026-06-26 | Wire gap analysis in.
TH-049 | Story | Export an explorable app map | Context: Graph Analytics | Context Analytics | Ankit | Backlog | 7 | 2026-06-29 | 2026-06-29 | Map for Gephi etc.
TH-050 | Story | Run the generated API tests in the runner | Execution | Core Loop | Nikhil Vemula | Backlog | 7 | 2026-06-29 | 2026-06-30 | Execute the API tests from the runner.
TH-051 | Story | Export a scenario tree diagram | Context: Graph Analytics | Context Analytics | Ankit | Backlog | 7 | 2026-06-30 | 2026-06-30 | Readable scenario tree.
TH-052 | Story | Define one unified results format | Execution | Core Loop | Nikhil Vemula | Backlog | 7 | 2026-07-01 | 2026-07-01 | Normalise API + UI outcomes into one file.
TH-053 | Story | Run map building in the scan | Context: Indexer/Scan | Context Analytics | Ankit | Backlog | 7 | 2026-07-01 | 2026-07-01 | Wire map building in.
TH-054 | Story | Add retry-once and flaky detection | Execution | Core Loop | Nikhil Vemula | Backlog | 7 | 2026-07-02 | 2026-07-02 | Re-run failures once, label flaky.
TH-055 | Story | Inject relevant notes into runs | Memory | Learning & Resilience | Ankit | Backlog | 7 | 2026-07-02 | 2026-07-02 | Feed notes into generation/execution.
TH-056 | Story | Consolidate + prune notes | Memory | Learning & Resilience | Ankit | Backlog | 8 | 2026-07-03 | 2026-07-03 | Merge duplicates, remove stale.
TH-057 | Story | Build the test-plan creator | Generation | Core Loop | Nikhil Vemula | Backlog | 8 | 2026-07-03 | 2026-07-06 | Decide scope + priority of what to test.
TH-058 | Story | Record heal events into memory | Execution | Learning & Resilience | Ankit | Backlog | 8 | 2026-07-06 | 2026-07-06 | Feed heal events into per-app memory.
TH-059 | Story | Derive UI scenarios from user flows | Generation | Core Loop | Nikhil Vemula | Backlog | 8 | 2026-07-07 | 2026-07-07 | Turn click-flows into scenarios.
TH-060 | Story | Add compose + run scripts | Infra: Deploy | Deployment & Scale | Ankit | Backlog | 8 | 2026-07-07 | 2026-07-07 | Easy container startup.
TH-061 | Story | Add quality + coverage checks | Generation | Core Loop | Nikhil Vemula | Backlog | 8 | 2026-07-08 | 2026-07-08 | Flag low-quality/low-coverage tests.
TH-062 | Story | Add optional AI quality-judge gate | Generation | Core Loop | Nikhil Vemula | Backlog | 8 | 2026-07-09 | 2026-07-09 | Optional AI review.
TH-063 | Story | Add a CI pipeline | Infra: Deploy | Deployment & Scale | Ankit | Backlog | 8 | 2026-07-08 | 2026-07-09 | Build/test on each change.
TH-064 | Story | De-duplicate findings across sources | Context: Graph Analytics | Context Analytics | Nikhil Vemula | Backlog | 9 | 2026-07-10 | 2026-07-13 | Match same endpoint/page across scans.
TH-065 | Story | Build self-service intake (URL + creds) | CLI | Deployment & Scale | Ankit | Backlog | 9 | 2026-07-10 | 2026-07-13 | Submit an app to start a run.
TH-066 | Story | Set up the analytics dependencies | Context: Graph Analytics | Context Analytics | Nikhil Vemula | Backlog | 9 | 2026-07-14 | 2026-07-14 | Add graph-analytics libraries.
TH-067 | Story | Bundle the graph viewer UI library locally | Context: Graph Viewer | Deployment & Scale | Ankit | Backlog | 9 | 2026-07-14 | 2026-07-14 | Graphs render offline.
TH-068 | Story | Load the app graph into the analytics engine | Context: Graph Analytics | Context Analytics | Nikhil Vemula | Backlog | 9 | 2026-07-15 | 2026-07-15 | Read the captured graph.
TH-069 | Story | Make browser install work offline | Crawler | Deployment & Scale | Ankit | Backlog | 9 | 2026-07-15 | 2026-07-15 | Pre-bundle the browser.
TH-070 | Story | Point installs at internal mirrors | Infra: Deploy | Deployment & Scale | Ankit | Backlog | 9 | 2026-07-16 | 2026-07-16 | Install deps from mirrors.
TH-071 | Story | Score importance + detect communities | Context: Graph Analytics | Context Analytics | Nikhil Vemula | Backlog | 9 | 2026-07-16 | 2026-07-17 | Rank important areas, cluster the app.
TH-072 | Story | Default to a local model in restricted mode | Infra: Model Connector | Deployment & Scale | Ankit | Backlog | 10 | 2026-07-17 | 2026-07-17 | Use local model when offline.
TH-073 | Story | Handle corporate certificate trust | Infra: Deploy | Deployment & Scale | Ankit | Backlog | 10 | 2026-07-20 | 2026-07-20 | Trust internal certificates.
TH-074 | Story | Group the app into named features | Context: Graph Analytics | Context Analytics | Nikhil Vemula | Backlog | 10 | 2026-07-20 | 2026-07-21 | Turn clusters into features.
TH-075 | Story | Fold the knowledge-sources folder into docs | Docs | Cleanup & Tests | Ankit | Backlog | 10 | 2026-07-21 | 2026-07-21 | Tidy the outdated placeholder.
TH-076 | Story | Remove the duplicate UI generator | Generation | Cleanup & Tests | Ankit | Backlog | 10 | 2026-07-22 | 2026-07-22 | Keep one source of truth.
TH-077 | Story | Find coverage gaps + untested areas | Context: Graph Analytics | Context Analytics | Nikhil Vemula | Backlog | 10 | 2026-07-22 | 2026-07-23 | Compare existing vs tested.
TH-078 | Story | Resolve the mock-data placeholder | Generation | Cleanup & Tests | Ankit | Backlog | 10 | 2026-07-23 | 2026-07-23 | Build or remove it.
TH-079 | Story | Define the per-app memory format | Memory | Learning & Resilience | Nikhil Vemula | Backlog | 11 | 2026-07-24 | 2026-07-24 | How learned knowledge is stored.
TH-080 | Story | Add tests for the extractors | Tests | Cleanup & Tests | Ankit | Backlog | 11 | 2026-07-24 | 2026-07-27 | Unit/smoke tests for extractors.
TH-081 | Story | Build the memory distiller core | Memory | Learning & Resilience | Nikhil Vemula | Backlog | 11 | 2026-07-27 | 2026-07-28 | Turn run outcomes into notes.
TH-082 | Story | Add tests for indexer + knowledge file | Tests | Cleanup & Tests | Ankit | Backlog | 11 | 2026-07-28 | 2026-07-28 | Tests for indexing + KB.
TH-083 | Story | Add tests for the test runner | Tests | Cleanup & Tests | Ankit | Backlog | 11 | 2026-07-29 | 2026-07-29 | Tests for the runner.
TH-084 | Story | Add distiller routing + storage | Memory | Learning & Resilience | Nikhil Vemula | Backlog | 11 | 2026-07-29 | 2026-07-30 | Route notes to the right files.
TH-085 | Story | Improve the safe-click crawling pass | Crawler | Cleanup & Tests | Ankit | Backlog | 11 | 2026-07-30 | 2026-07-30 | Refine which buttons are clicked.
TH-086 | Story | Update the architecture overview | Docs | Deployment & Scale | Ankit | Backlog | 12 | 2026-07-31 | 2026-07-31 | Refresh the architecture doc.
TH-087 | Story | Add recall tools to fetch notes | Infra: Agentic Harness | Learning & Resilience | Nikhil Vemula | Backlog | 12 | 2026-07-31 | 2026-08-03 | Look up relevant notes.
TH-088 | Story | Document the knowledge base + schema | Docs | Deployment & Scale | Ankit | Backlog | 12 | 2026-08-03 | 2026-08-03 | How the knowledge file works.
TH-089 | Story | Write the CLI command reference | Docs | Deployment & Scale | Ankit | Backlog | 12 | 2026-08-04 | 2026-08-04 | scan/generate/run/report/plan.
TH-090 | Story | Build self-healing locator fallbacks | Execution | Learning & Resilience | Nikhil Vemula | Backlog | 12 | 2026-08-04 | 2026-08-05 | Deterministic alternates first.
TH-091 | Story | Document execution + reporting | Docs | Deployment & Scale | Ankit | Backlog | 12 | 2026-08-05 | 2026-08-05 | How runs + reports work.
TH-092 | Story | Document the analytics module | Docs | Deployment & Scale | Ankit | Backlog | 12 | 2026-08-06 | 2026-08-06 | Importance/features/gaps.
TH-093 | Story | Add AI-assisted locator resolve | Execution | Learning & Resilience | Nikhil Vemula | Backlog | 12 | 2026-08-06 | 2026-08-07 | AI suggests an alternate when an element moves.
TH-094 | Story | Document the memory module | Docs | Deployment & Scale | Ankit | Backlog | 13 | 2026-08-07 | 2026-08-07 | Per-app skill memory.
TH-095 | Story | Document self-healing execution | Docs | Deployment & Scale | Ankit | Backlog | 13 | 2026-08-10 | 2026-08-10 | How healing works + limits.
TH-096 | Story | Capture the page state for healing | Execution | Learning & Resilience | Nikhil Vemula | Backlog | 13 | 2026-08-10 | 2026-08-11 | Snapshot roles/labels/text.
TH-097 | Story | Write the onboarding guide (add an app) | Docs | Deployment & Scale | Ankit | Backlog | 13 | 2026-08-11 | 2026-08-12 | How a tester onboards a new app.
TH-098 | Story | Add heal cache + retry logic | Execution | Learning & Resilience | Nikhil Vemula | Backlog | 13 | 2026-08-12 | 2026-08-13 | Remember a successful fix.
TH-099 | Story | Document the test strategy + 3 gates | Docs | Deployment & Scale | Ankit | Backlog | 13 | 2026-08-13 | 2026-08-13 | Authenticity/session-safety/self-repair.
TH-100 | Story | Add sandboxed setup/teardown hooks | Execution | Learning & Resilience | Nikhil Vemula | Backlog | 14 | 2026-08-14 | 2026-08-17 | Run hooks in an isolated container.
TH-101 | Story | Build the container image | Infra: Deploy | Deployment & Scale | Nikhil Vemula | Backlog | 14 | 2026-08-18 | 2026-08-19 | Worker image for the tool.
TH-102 | Story | Bug-fix & stabilization buffer 2 | Generation | Stabilization & Release | Ankit | Backlog | 14 | 2026-08-14 | 2026-08-20 | Stabilization / UAT / release.
TH-103 | Story | Make outputs per-app (no collisions) | Context: Indexer/Scan | Deployment & Scale | Nikhil Vemula | Backlog | 14 | 2026-08-20 | 2026-08-21 | Parallel apps without overwriting.
TH-104 | Story | Add a job queue + workers | Infra: Deploy | Deployment & Scale | Nikhil Vemula | Backlog | 15 | 2026-08-24 | 2026-08-25 | Process many runs in parallel.
TH-105 | Story | Add proxy support to crawler + browser | Crawler | Deployment & Scale | Nikhil Vemula | Backlog | 15 | 2026-08-26 | 2026-08-26 | Reach targets via corporate proxy.
TH-106 | Story | Add AI button classification for crawling | Crawler | Cleanup & Tests | Nikhil Vemula | Backlog | 15 | 2026-08-27 | 2026-08-28 | Classify safe/unsafe buttons.
TH-107 | Story | UAT support & feedback fixes | Execution | Stabilization & Release | Ankit | Backlog | 15 | 2026-08-21 | 2026-08-28 | Stabilization / UAT / release.
TH-108 | Story | Write the restricted/offline deploy guide | Docs | Deployment & Scale | Nikhil Vemula | Backlog | 16 | 2026-08-31 | 2026-09-01 | Mirrors, local models, offline.
TH-109 | Story | Write the egress / NetSec proposal | Docs | Deployment & Scale | Nikhil Vemula | Backlog | 16 | 2026-09-02 | 2026-09-02 | Allow-list + approval process.
TH-110 | Story | Build the KT / handover pack | Docs | Deployment & Scale | Nikhil Vemula | Backlog | 16 | 2026-09-03 | 2026-09-04 | Knowledge transfer + handover.
TH-111 | Story | Regression suite + smoke pack | Tests | Stabilization & Release | Ankit | Backlog | 16 | 2026-08-31 | 2026-09-04 | Stabilization / UAT / release.
TH-112 | Story | Integration test pass (end-to-end) | Execution | Stabilization & Release | Nikhil Vemula | Backlog | 17 | 2026-09-07 | 2026-09-11 | Stabilization / UAT / release.
TH-113 | Story | Documentation & KT polish | Docs | Stabilization & Release | Ankit | Backlog | 17 | 2026-09-07 | 2026-09-11 | Stabilization / UAT / release.
TH-114 | Story | Bug-fix & stabilization buffer 1 | Generation | Stabilization & Release | Nikhil Vemula | Backlog | 18 | 2026-09-14 | 2026-09-18 | Stabilization / UAT / release.
TH-115 | Story | Performance & load hardening | Execution | Stabilization & Release | Nikhil Vemula | Backlog | 19 | 2026-09-21 | 2026-09-24 | Stabilization / UAT / release.
TH-116 | Story | Security review & remediation | Infra: Deploy | Stabilization & Release | Nikhil Vemula | Backlog | 20 | 2026-09-25 | 2026-09-30 | Stabilization / UAT / release.
TH-117 | Story | Scaffold the web dashboard | CLI | Deployment & Scale | Ankit | Deferred (post Sep 30) | 20 | 2026-10-01 | 2026-10-02 | Initial web UI (deferred).
TH-118 | Story | Design a database-backed knowledge store | Infra: DB | Deployment & Scale | Nikhil Vemula | Deferred (post Sep 30) | 20 | 2026-10-01 | 2026-10-02 | Plan the DB schema (optional).
TH-119 | Story | Production cutover + handover sign-off | Infra: Deploy | Stabilization & Release | Nikhil Vemula | Backlog | 20 | 2026-10-01 | 2026-10-06 | Stabilization / UAT / release.
TH-120 | Story | Build the web results view | CLI | Deployment & Scale | Ankit | Deferred (post Sep 30) | 21 | 2026-10-05 | 2026-10-06 | Browse results in the UI (deferred).
TH-121 | Story | Implement the database store | Infra: DB | Deployment & Scale | Nikhil Vemula | Deferred (post Sep 30) | 21 | 2026-10-05 | 2026-10-06 | Replace file store with DB (optional).
TH-122 | Story | Backlog grooming + estimation (ongoing) | Project Mgmt | Project Management | Nikhil Kalsi | Backlog | 1 | 2026-05-15 | 2026-10-07 | Recurring refinement.
TH-123 | Story | Sprint demos + stakeholder reporting | Project Mgmt | Project Management | Nikhil Kalsi | Backlog | 1 | 2026-05-15 | 2026-10-07 | Bi-weekly demos + status.
TH-124 | Story | Track risks + external dependencies | Project Mgmt | Project Management | Nikhil Kalsi | Backlog | 1 | 2026-05-15 | 2026-10-07 | NetSec, specs, test accounts.
TH-125 | Story | Release + UAT coordination | Project Mgmt | Project Management | Nikhil Kalsi | Backlog | 19 | 2026-09-21 | 2026-10-07 | Final release + handover.

## Summary
Owner | Total | Done | Backlog | Deferred | Start | End
Nikhil Vemula | 65 | 21 | 42 | 2 | 2026-05-15 | 2026-10-06
Ankit | 55 | 0 | 53 | 2 | 2026-05-15 | 2026-09-11
Nikhil Kalsi | 5 | 0 | 5 | 0 | 2026-05-15 | 2026-10-07
TOTAL / Deadline | 125 | 21 | 100 | 4 | 2026-05-15 | 2026-09-30